## Project Schedule and WBS
| TEAM ADNA | Project: Green ICT Application
Tasks |  | Person | Start date | Finish date | Status | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-04 | 2017-11-05 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15 | 2017-12-16
Document writing |  | Anh Le | 2017-10-06 | 2017-12-07
| Project plan |  | 2017-10-06 | 2017-11-02 | Finished | [11 empty] | Start |  |  |  |  | End
| Schedule plan |  | 2017-10-06 | 2017-11-02 | Finished | [14 empty] | Start | [45 empty] | End
| Project report |  | 2017-11-20 | 2017-12-05 | Finished | [54 empty] | Start |  |  |  |  | End
| User manual |  | 2017-11-20 | 2017-12-05 | Finished | [54 empty] | Start |  |  |  |  | End
| Peer evaluation |  | 2017-12-07 | 2017-12-07 | Finished | [61 empty] | Start |  | End
Database implementation |  | An Pham, Nguyen Tran | 2017-10-13 | 2017-11-02
| Design database |  | 13/10/2017 | 2017-11-01 | Finished | [13 empty] | Start | [13 empty] | End
| Database specification, ER - model |  | 13/10/2017 | 2017-11-01 | Finished | [13 empty] | Start | [13 empty] | End
| Creating database in Localhost |  | 13/10/2017 | 2017-11-01 | Finished | [18 empty] | Start | [11 empty] | End
API |  | Nguyen Tran, An Pham | 2017-10-13 | 2017-11-02
| Design UML - model |  | 2017-10-13 | 2017-11-02 | Finished | [13 empty] | Start | [13 empty] | End
| Create API |  | 2017-10-14 | 2017-11-10 | Finished | [19 empty] | Start | [11 empty] | End
| Creating application structure |  | 2017-10-10 | 2017-11-11 | Finished | [5 empty] | Start | [9 empty] | End
| Connect to database |  | 2017-10-16 | 2017-11-12 | Finished | [27 empty] | Start | [9 empty] | End
| Connect to UI |  | 2017-10-17 | 2017-12-04 | Finished | [27 empty] | Start | [30 empty] | End
Designing UI/UX |  | Duc Pham | 2017-10-13 | 2017-11-20
| Create UI using WPF |  | 2017-10-14 | 2017-11-15 | Finished | [9 empty] | Start | [46 empty] | End
| Create link between UI pages |  | 2017-10-15 | 2017-11-18 | Finished | [36 empty] | Start | [7 empty] | End
| Connect to application |  | 2017-10-16 | 2017-11-18 | Finished | [34 empty] | Start | [8 empty] | End
| Creating event handler |  | 2017-10-17 | 2017-11-30 | Finished | [36 empty] | Start | [19 empty] | End
| Design UX |  | 2017-10-18 | 2017-11-30 | Finished | [43 empty] | Start | [10 empty] | End
Finished
Testing our project |  | Anh Le, Duc Pham, Nguyen Tran, An Pham | 2017-11-09 | 2017-12-01 | Finished
| Upload prototype application |  | 11/31/2017 | 2017-12-01 | Finished
| Test the application |  | 2017-12-01 | 2017-12-04 | Finished